## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As a user, I want the project environment to be set up so that development can start smoothly. | Must | NA | Mayank | Done
Sprint 1 | Sprint 1 | US-02 | As a system, I want core mathematical logic and risk formulas so that calculations are accurate. | Must | Depends on US-01 | Chetana | Done
Sprint 1 | Sprint 1 | US-03 | As a system, I want API integration to fetch cryptocurrency data. | Must | Depends on US-01 | Shivani | Done
Sprint 1 | Sprint 1 | US-04 | As a system, I want a database structure to store portfolio data. | Must | Depends on US-03 | Shivani | Done
Sprint 1 | Sprint 2 | US-05 | As a user, I want a basic frontend dashboard for portfolio visualization. | Must | Depends on US-04 | Annapurna | Done
Sprint 1 | Sprint 3 | US-06 | As a team, we want proper documentation so that the project is easy to understand. | Should | NA | Shivani | Done
Sprint 2 | Sprint 4 | US-07 | As a system, I want log return calculations from historical data so that portfolio performance can be measured. | Must | Depends on US-02 | Chetana | Done
Sprint 2 | Sprint 5 | US-08 | As a system, I want Monte Carlo simulation to find optimal portfolio weights. | Must | Depends on US-07 | Mayank | Done
Sprint 2 | Sprint 6 | US-09 | As a system, I want multiprocessing to speed up the simulation trials. | Must | Depends on US-08 | Chetana | Done
Sprint 2 | Sprint 7 | US-10 | As a user, I want a Portfolio Mixer UI with coin selection and investment input to generate an optimization request. | Must | Depends on US-05 | Mayank | Done
Sprint 2 | Sprint 8 | US-11 | As a system, I want a backend API endpoint to connect the frontend request to the optimization engine. | Must | Depends on US-09 | Annapurna | Done
Sprint 3 | Sprint 9 | US-12 | As a user, I want signup and login functionality so that my portfolio data is secure. | Must | Depends on backend | Annapurna | Done
Sprint 3 | Sprint 10 | US-13 | As a user, I want to view saved portfolio mixes on a dashboard so that I can track my history. | Must | Depends on US-12 | Annapurna | Done
Sprint 3 | Sprint 11 | US-14 | As a user, I want live cryptocurrency price monitoring so that I can track market changes. | Must | Depends on API integration | Mayank | Done
Sprint 3 | Sprint 12 | US-15 | As a user, I want to update or delete portfolio assets so that I can manage my investments. | Must | Depends on US-13 | Mayank | Done
Sprint 3 | Sprint 13 | US-16 | As a system, I want risk status indicators (Stable/Warning/Danger) so that the user understands market risk quickly. | Must | Depends on live price data | Chetana | Done
Sprint 3 | Sprint 14 | US-17 | As a user, I want to download a portfolio report in CSV format so that I can analyze it offline. | Must | Depends on US-13 | Shivani | Done
Sprint 4 | Sprint 15 | US-18 | As a system, I want a backend rule engine to rebalance investments automatically when market conditions change. | Must | Depends on core calculator | Shivani | Done
Sprint 4 | Sprint 16 | US-19 | As a system, I want threshold-based reallocation during volatility so that funds are spread safely. | Must | Depends on US-18 | Annapurna | Done
Sprint 4 | Sprint 17 | US-20 | As a user, I want API endpoints to save and trigger rebalancing rules from the frontend. | Must | Depends on US-19 | Shivani | Done
Sprint 4 | Sprint 18 | US-21 | As a user, I want UI controls (slider/toggle) to set risk appetite so that I can control the strategy. | Must | Depends on backend rules | Mayank | Done
Sprint 4 | Sprint 19 | US-22 | As a user, I want dynamic visual feedback to understand how rules rebalance my investments. | Must | Depends on US-21 | Mayank | Done
Sprint 4 | Sprint 20 | US-23 | As a system, I want stress testing in bull, bear, and volatile markets to validate rule logic. | Must | Depends on rule engine | Chetana | Done
Sprint 4 | Sprint 21 | US-24 | As a system, I want stable handling of extreme market conditions without crashes or incorrect outputs. | Must | Depends on US-23 | Chetana | Done
Sprint 4 | Sprint 22 | US-25 | As a team, we want final project documentation and review completion. | Must | NA | Shivani | Done
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 143 | 28 | 24 | 9 | 14 | 5 | 1 | 19 | 0 | 3 | 13 | 0 | 4 | 0 | 21
SPRINT 1 BACKLOG
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity
US-01 | S1-T1 | Project environment setup | 2026-01-01 | 2026-01-01 | Mayank | Development | Done | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
US-02 | S1-T2 | Core math & risk formulas setup | 2026-01-02 | 2026-01-03 | Chetana | Development | Done | 6 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1
US-03 | S1-T3 | API integration basic setup | 2026-01-03 | 2026-01-04 | Shivani | Development | Done | 4 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
US-04 | S1-T4 | Database structure creation | 2026-01-04 | 2026-01-05 | Shivani | Development | Done | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
US-05 | S1-T5 | Basic frontend dashboard UI | 2026-01-05 | 2026-01-06 | Annapurna | UI Design | Done | 5 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
US-06 | S1-T6 | Project documentation | 2026-01-06 | 2026-01-06 | Shivani | Documentation | Done | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
US-07 | S2-T1 | Log returns calculation from dataset | 2026-01-08 | 2026-01-09 | Chetana | Development | Done | 6 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1
US-08 | S2-T2 | Monte Carlo simulation implementation | 2026-01-10 | 2026-01-11 | Chetana | Development | Done | 8 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 1
US-09 | S2-T3 | Multiprocessing for parallel trials | 2026-01-12 | 2026-01-13 | Chetana | Development | Done | 8 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1
US-10 | S2-T4 | Portfolio Mixer UI inputs (coins + amount) | 2026-01-09 | 2026-01-10 | Mayank | UI Design | Done | 6 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1
US-11 | S2-T5 | FastAPI endpoint to connect UI and engine | 2026-01-13 | 2026-01-14 | Annapurna | Integration | Done | 6 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1
US-12 | S3-T1 | Signup & login functionality | 2026-01-15 | 2026-01-16 | Annapurna | Development | Done | 8 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 1
US-13 | S3-T2 | Dashboard saved portfolio history view | 2026-01-17 | 2026-01-18 | Annapurna | UI Design | Done | 6 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1
US-14 | S3-T3 | Live crypto price monitoring integration | 2026-01-16 | 2026-01-17 | Mayank | Development | Done | 6 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1
US-15 | S3-T4 | Update/Delete portfolio assets UI flow | 2026-01-18 | 2026-01-19 | Mayank | Development | Done | 6 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1
US-16 | S3-T5 | Risk status indicators logic (Stable/Warning/Danger) | 2026-01-19 | 2026-01-20 | Chetana | Testing | Done | 6 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1
US-17 | S3-T6 | CSV report generation endpoint | 2026-01-20 | 2026-01-20 | Shivani | Development | Done | 4 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
US-18 | S4-T1 | Backend rule engine for rebalancing | 2026-01-22 | 2026-01-23 | Shivani | Development | Done | 8 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 1
US-19 | S4-T2 | Threshold-based reallocation integration | 2026-01-24 | 2026-01-25 | Shivani | Development | Done | 6 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1
US-20 | S4-T3 | API endpoints to save/trigger rules | 2026-01-25 | 2026-01-26 | Shivani | Development | Done | 6 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1
US-21 | S4-T4 | UI controls for risk appetite (slider/toggle) | 2026-01-23 | 2026-01-24 | Mayank | UI Design | Done | 6 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1
US-22 | S4-T5 | Dynamic visual feedback for rule impact | 2026-01-26 | 2026-01-27 | Mayank | UI Design | Done | 5 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0
US-23 | S4-T6 | Stress testing bull/bear/volatile scenarios | 2026-01-27 | 2026-01-28 | Chetana | Testing | Done | 8 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-24 | S4-T7 | Validate stability under extreme conditions | 2026-01-28 | 2026-01-29 | Chetana | Testing | Done | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-25 | S4-T8 | Final documentation and review | 2026-01-29 | 2026-01-29 | Shivani | Documentation | Done | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Setting up environment and dependencies took time. | Installed required libraries and fixed version issues.
Sprint 1 | Day 2 | API keys / endpoint confusion while fetching crypto data. | Verified API documentation and tested sample requests.
Sprint 1 | Day 3 | Database connection and schema planning issues. | Designed collection structure and tested insert/read operations.
Sprint 1 | Day 4 | UI alignment issues in dashboard layout. | Fixed CSS and adjusted component structure.
Sprint 2 | Day 1 | Log return calculation mismatch in dataset format. | Cleaned dataset and validated calculations with sample values.
Sprint 2 | Day 2 | Monte Carlo simulation was running slow. | Optimized code and reduced unnecessary computations.
Sprint 2 | Day 3 | Multiprocessing errors while running parallel trials. | Handled process pooling and fixed concurrency issues.
Sprint 3 | Day 1 | Login/session flow was unclear for dashboard access. | Defined authentication flow and tested user sessions.
Sprint 4 | Day 1 | Rule engine logic needed clarity for rebalancing thresholds. | Finalized rule conditions and tested with sample scenarios.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-11-12 | 2025-11-25 | Annapurna | Plan backend API flow before UI integration | Delaying integration till the end | Coordinating modules and integration | Mid-sprint integration testing with frontend and math engine
2 | Sprint 1 | 2025-11-12 | 2025-11-25 | Mayank | Design UI layout and components early | Ignoring responsive testing initially | Creating clean UI screens | Test UI on mobile and desktop breakpoints
3 | Sprint 2 | 2025-11-26 | 2025-12-09 | Chetana | Validate dataset format before calculations | Running simulation without optimization | Using correct log return calculations | Add performance optimization and sanity checks
4 | Sprint 2 | 2025-11-26 | 2025-12-09 | Shivani | Maintain documentation during development | Leaving documentation for last minute | Writing clear documentation and flow notes | Update README and module-wise documentation
5 | Sprint 3 | 2025-12-10 | 2025-12-24 | Annapurna | Add error handling and retries in API responses | Skipping backend validation | Regular API + DB integration | Implement validation + stable response mapping
6 | Sprint 3 | 2025-12-10 | 2025-12-24 | Mayank | Add meaningful UI feedback and results visualization | Hardcoding UI values | Making reusable UI components | Improve UX with clear charts and user inputs
7 | Sprint 4 | 2025-12-25 | 2026-01-13 | Chetana | Start stress testing with bull/bear/volatile scenarios early | Testing only normal scenarios | Validating math outputs carefully | Add edge-case tests and stability verification
8 | Sprint 4 | 2025-12-25 | 2026-01-13 | Shivani | Add rule engine thresholds and API trigger endpoints early | Keeping logic scattered without structure | Implementing backend logic cleanly | Finalize rule module + API endpoints for spreading rules